# PL-01 · Meeting Room Booking Study - Research Plan

| Field | Value |
| --- | --- |
| ID | PL-01 |
| Type | Research plan |
| Study | S-01 Meeting Room Booking Study |
| Status | Final |
| Author | Maya Alvarez |
| Date | 2026-09-08 |
| Last reviewed | 2026-10-05 |
| Related | N-01 Interview notes, A-01 Room usage summary, R-01 Readout |

Fictional demo data. Harborview Group, RoomBook and all people in this record are invented.

## Background

Harborview Group is a fictional company with about 400 people at one headquarters site. Staff book the site’s 8 meeting rooms (4 on floor 2, 4 on floor 3) in RoomBook, an internal web app that is separate from the Outlook calendar. The office manager reported a steady stream of complaints that rooms look booked but are empty. This study looks at what people struggle with when booking a room and what they do about it.

## Research questions

- What are the main pain points people have when booking a meeting room?

- How do people work around each pain point?

- What did we not expect to learn?

## Method

- Interviews: 6 semi-structured interviews, remote, 30 to 45 minutes each, one participant per session, run by Maya Alvarez. Notes are in N-01.

- Usage data: a pull of RoomBook bookings and door-sensor occupancy for all 8 rooms, 2026-09-08 to 2026-09-19 (10 working days). Summarized in A-01.

## Participants

Six employees, chosen to cover different ways of using the rooms: an office manager, a project manager, a software engineer, a sales representative who is in the office two days a week, an executive assistant who books for three executives, and a new hire three weeks into the job.

## Schedule

| Date | Activity |
| --- | --- |
| 2026-09-08 | Plan finalized, usage data window opens |
| 2026-09-15 to 2026-09-17 | Six interviews, two per day |
| 2026-09-19 | Usage data window closes |
| 2026-09-24 | Findings F-01 to F-05 written |
| 2026-10-02 | Readout R-01 |

## Out of scope

Room equipment faults, catering, visitor access, and any room outside the headquarters site.

## What this study can and cannot answer

Six interviews show what kinds of problems exist and how people cope. They do not show how common each problem is across all 400 staff. The usage data shows how rooms were used, not why.